{"text_format":"3","workbook":"xls","n_sheets":4,"sheets":["2018年实事工程","空白表","拍而未建工业项目","审而未供工业项目"],"not_rendered":{"external_links":1,"defined_names":4},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"2018年实事工程","index":0,"n_rows":140,"n_cols":10,"rows_kept":140,"merged":[[0,0,0,1],[1,0,1,9]],"flags":["formulas_cached_only"]}
["附件："]
["相城区2018年政府实事工程任务分解表"]
["序号","项目名称","建设起止年限","计划总投资（万元）","项目规模及主要内容","2018年计划投资（万元）","2018年实施内容及完成形象进度","计划实施时间(年月）","主办单位","实施单位"]
[null,"合  计",null,{"v":1610406.95,"d":"1610407"},null,{"v":410792.95,"d":"410793"}]
["一","创业就业提升工程",null,5220,null,5220]
[1,"创业就业提升工程",2018,5220,"持续推进就业优先战略，开发就业岗位，提高高校毕业生就业率，扶持重点群体就业，控制城镇登记失业率；大力推进创业带动就业工作；大力扶持人力资源产业园“一园三中心”发展",5220,"提供就业岗位4.0万个，本区户籍高校毕业生年末总体就业率95%以上，困难家庭失业人员动态清零，城镇登记失业率控制在3%以内。开展创业培训750人、职业培训1.2万人，扶持本区户籍市民、大学生创业1000人；举办青年创新创业大赛，奖励青年创新创业项目15个；新增技能大师工作室3家以上，乡镇板块创业孵化载体全覆盖。落实各项就业创业补贴政策，多项补贴资金及时核发兑现。大力扶持人力资源产业园“一园三中心”发展",2018.01,"区人社局","区人社局"]
["二","基础教育提升工程",null,106788,null,31887]
[2,"相城第三实验中学","2018-2019",32500,"新建18轨初中，建筑面积约6.5万平方米",7000,"主体结构封顶",2018.06,"区教育局","区城投集团"]
[3,"太平中学（暂定名）","2018-2019",26520,"新建12轨初中，建筑面积约6.1万平方米",9890,"主体结构封顶，土建完成50%",2018.06,"区教育局","高铁新城"]
[4,"高铁新城第三幼儿园（暂定名）","2018-2019",5368,"新建7轨幼儿园，建筑面积约1万平方米",1997,"主体结构封顶，土建完成50%",2018.06,"区教育局","高铁新城"]
[5,"漕湖幼儿园","2017-2018",5400,"新建6轨幼儿园，建筑面积约1.1万平方米",2000,"完成装饰及相关配套工作，竣工投入使用",2017.05,"区教育局","开发区"]
[6,"北桥中学","2016-2018",22000,"新建16轨初中，建筑面积约4.8万平方米",9000,"完成装饰及相关配套工作，9月交付使用",2016.06,"区教育局","开发区"]
[7,"黄桥中学","2016-2018",15000,"新建14轨初中，建筑面积约4万平方米",2000,"完成装饰及操场等配套工程，9月交付使用",2016.08,"区教育局","黄桥街道"]
["三","健康服务提升工程",null,{"v":1539.45,"d":"1539"},null,{"v":1329.45,"d":"1329"}]
[8,"健康市民“531”行动计划","2018-2019",280,"开展对55-60岁户籍居民心脑血管疾病筛查。规范慢性呼吸病病人管理，有效减少住院次数 ",220,"完成我区55-60岁户籍居民心脑血管疾病筛查。2018年底完成慢性呼吸病筛选1000例，规范管理100例",2018.01,"区卫计局","各医疗机构"]
[9,"儿童健康工程（婴幼儿健康筛查、儿童口腔幸福工程、公共场所母乳哺育）",2018,90,"通过实施婴幼儿健康筛查工程，预防儿童口腔疾病，提高儿童健康水平。落实《苏州市公共场所母乳哺育室设施建设促进办法》，推动在城乡公共场所普设母乳哺育室，保障妇女权益",90,"高危儿童筛查率达到100%；完成2500人次窝沟封闭；在相城区城乡范围内建立9家公共场所母乳哺育室（其中含旅游厕所中3家），并投入使用",2018.01,"区卫计局、旅游局、妇联","各医疗机构、相关单位"]
[10,"健康卫士“531”行动计划",2018,400,"加快卫计监督在线监测信息共享平台建设，完成放射防护、医疗废物、饮用水水质、游泳场馆水质在线监测和移动监管",250,"完成放射防护、医疗废物、饮用水水质、游泳场馆水质在线监测和移动监管建设",2018.01,"区卫计局","区卫生监督所"]
[11,"健康城市“531”扩大免疫规划项目（水痘疫苗免费接种）",2018,72,"对2016年7月1日后出生的户籍儿童、居住满3个月的流动儿童免费接种水痘疫苗",72,"完成8000人次左右的水痘疫苗接种",2018.01,"区卫计局","各医疗机构"]
[12,"残疾人康复工程",2018,190,"“残疾人之家”建设工程；开展学生脊柱侧弯筛查工程；实施个性化辅具适配工程",190,"10家“残疾人之家”建设工程；完成学生脊柱侧弯筛查7000例；为400位残疾人进行个性化辅具适配",null,"区残联","所涉镇（区、街道）"]
["⑴","“残疾人之家”标准化建设工程（元和街道）",2018,15,"御窑残疾人之家标准化建设",15,"御窑残疾人之家标准化建设",2018.03,"区残联","元和街道"]
["⑵","“残疾人之家”标准化建设工程（渭塘镇）",2018,15,"渭塘残疾人之家标准化建设",15,"渭塘残疾人之家标准化建设",2018.03,"区残联","渭塘镇"]
["⑶","“残疾人之家”标准化建设工程（北桥街道）",2018,15,"丰泾残疾人之家标准化建设",15,"丰泾残疾人之家标准化建设",2018.03,"区残联","北桥街道"]
["⑷","“残疾人之家”标准化建设工程（太平街道）",2018,15,"青漪残疾人之家标准化建设",15,"青漪残疾人之家标准化建设",2018.03,"区残联","太平街道"]
["⑸","“残疾人之家”标准化建设工程（阳澄湖镇）",2018,15,"岸山残疾人之家标准化建设",15,"岸山残疾人之家标准化建设",2018.03,"区残联","阳澄湖镇"]
["⑹","“残疾人之家”标准化建设工程（黄桥街道）",2018,15,"张庄残疾人之家标准化建设",15,"张庄残疾人之家标准化建设",2018.03,"区残联","黄桥街道"]
["⑺","“残疾人之家”标准化建设工程（高新区（筹））",2018,15,"高新区（筹）残疾人之家标准化建设",15,"高新区（筹）残疾人之家标准化建设",2018.03,"区残联","高新区（筹）"]
["⑻","“残疾人之家”标准化建设工程（望亭镇）",2018,15,"鹤溪残疾人之家标准化建设",15,"鹤溪残疾人之家标准化建设",2018.03,"区残联","望亭镇"]
["⑼","“残疾人之家”标准化建设工程（度假区）",2018,15,"度假区残疾人之家标准化建设",15,"度假区残疾人之家标准化建设",2018.03,"区残联","度假区"]
["⑽","“残疾人之家”标准化建设工程（澄阳街道）",2018,15,"泰元残疾人之家标准化建设",15,"泰元残疾人之家标准化建设",2018.05,"区残联","澄阳街道"]
["⑾","脊柱侧弯筛查工程",2018,6,"完成学生脊柱侧弯筛查7000例",6,"完成学生脊柱侧弯筛查7000例",2018.05,"区残联","区残联"]
["⑿","个性化辅具适配工程",2018,34,"为400位残疾人进行个性化辅具适配",34,"为400位残疾人进行个性化辅具适配",2018.05,"区残联","区残联"]
["13","文化体育设施建设",null,{"v":507.45,"d":"507"},"建设街道文体中心1个、社区综合性文化服务中心5个；健身步道15.3km、场馆450m²",{"v":507.45,"d":"507"},"全部完成",null,"区文体局","所涉镇（区、街道）"]
["⑴","文化体育设施建设（开发区）","2018",100,"建设场馆200m²（澄阳星湖花海）",100,"完成","2018.07","区文体局","开发区"]
["⑵","文化体育设施建设（元和街道）","2018",14,"社区综合性文化服务中心3个（华成社区、御苑社区、蠡口社区）；健身步道（小外滩）5km、场馆250m²（古元路文体中心）",14,"完成","2018.03","区文体局","元和街道"]
["⑶","文化体育设施建设（黄桥街道）","2018",100,"社区综合性文化服务中心1个（荷馨苑）",100,"完成","2018.01","区文体局","黄桥街道"]
["⑷","文化体育设施建设（太平街道）","2018",200,"街道文体中心1个（文创园）",200,"完成","2018.01","区文体局","太平街道"]
["⑸","文化体育设施建设（渭塘镇）","2017-2018",65,"社区综合性文化服务中心1个（钻石家园社区）；健身步道（朗悦湾小区）3km",65,"完成","2017.11","区文体局","渭塘镇"]
["⑹","文化体育设施建设（阳澄湖镇）","2018",25,"健身步道（阳澄湖镇市民运动公园、湘苑社区）5km",25,"完成","2018.05","区文体局","阳澄湖镇"]
["⑺","文化体育设施建设（望亭镇）","2018",{"v":3.45,"d":"3"},"健身步道（运河路）2.3km",{"v":3.45,"d":"3"},"完成","2018.01","区文体局","望亭镇"]
["四","环境整治提升工程",null,{"v":168503.5,"d":"168504"},null,{"v":80183.5,"d":"80184"}]
[14,"大气污染治理工程",null,null,"全年淘汰整治燃煤锅炉9家、重点VOCS排放企业77家",null,"完成",null,"区环保局","所涉镇（区、街道）"]
["⑴","大气污染治理工程（元和街道）",null,null,"全年关停重点VOCS排放企业3家",null,"完成",null,"区环保局","元和街道"]
["⑵","大气污染治理工程（澄阳街道）",null,null,"全年关停重点VOCS排放企业16家",null,"完成",null,"区环保局","澄阳街道"]
["⑶","大气污染治理工程（北桥街道）",null,null,"全年关停整治燃煤锅炉1家、重点VOCS排放企业6家",null,"完成",null,"区环保局","北桥街道"]
["⑷","大气污染治理工程（漕湖街道）",null,null,"全年关停重点VOCS排放企业4家",null,"完成",null,"区环保局","漕湖街道"]
["⑸","大气污染治理工程（黄桥街道）",null,null,"全年关停重点VOCS排放企业3家",null,"完成",null,"区环保局","黄桥街道"]
["⑹","大气污染治理工程（太平街道）",null,null,"全年关停重点VOCS排放企业1家",null,"完成",null,"区环保局","太平街道"]
["⑺","大气污染治理工程（高新区（筹））",null,null,"全年关停整治燃煤锅炉2家、重点VOCS排放企业11家",null,"完成",null,"区环保局","高新区（筹）"]
["⑻","大气污染治理工程（望亭镇）",null,null,"全年关停重点VOCS排放企业12家",null,"完成",null,"区环保局","望亭镇"]
["⑼","大气污染治理工程（渭塘镇）",null,null,"全年关停整治燃煤锅炉6家、重点VOCS排放企业14家",null,"完成",null,"区环保局","渭塘镇"]
["⑽","大气污染治理工程（阳澄湖镇）",null,null,"全年关停重点VOCS排放企业7家",null,"完成",null,"区环保局","阳澄湖镇"]
[15,"水环境保护工程",null,null,"全年淘汰整治电镀（线路板）企业16家、印染企业35家、化工企业2家、金属表面处理(酸洗、铝氧化、喷涂等)企业22家",null,"完成",null,"区环保局、区经信局","所涉镇（区、街道）"]
["⑴","水环境保护工程（北桥街道）",null,null,"全年淘汰整治印染企业13家、金属表面处理(酸洗、铝氧化、喷涂等)企业2家",null,"完成",null,"区环保局","北桥街道"]
["⑵","水环境保护工程（黄桥街道）",null,null,"全年淘汰整治电镀（线路板）企业13家、金属表面处理(酸洗、铝氧化、喷涂等)企业6家",null,"完成",null,"区环保局","黄桥街道"]
["⑶","水环境保护工程（高新区（筹））",null,null,"全年关停整治印染企业1家，化工企业2家、金属表面处理(酸洗、铝氧化、喷涂等)企业2家",null,"完成",null,"区环保局、区经信局","高新区（筹）"]
["⑷","水环境保护工程（望亭镇）",null,null,"全年淘汰整治电镀（线路板）企业1家、金属表面处理(酸洗、铝氧化、喷涂等)2家",null,"完成",null,"区环保局、区经信局","望亭镇"]
["⑸","水环境保护工程（渭塘镇）",null,null,"全年淘汰整治电镀（线路板）企业2家、印染企业11家、金属表面处理(酸洗、铝氧化、喷涂等)企业9家",null,"完成",null,"区环保局","渭塘镇"]
["⑹","水环境保护工程（阳澄湖镇）",null,null,"全年淘汰整治印染企业10家、金属表面处理(酸洗、铝氧化、喷涂等)企业1家",null,"完成",null,"区环保局、区经信局","阳澄湖镇"]
[16,"城区控源截污工程","2017-2018",10000,"对元和、澄阳、黄桥进行控源截污建设和改造",10000,"完成",2018.01,"区水利局","区水务集团 、元和街道、黄桥街道、开发区"]
["⑴","城区元和街道控源截污工程","2017-2018",5300,"对元和街道进行控源截污建设和改造",5300,"完成",2018.01,"区水利局","区水务集团、元和街道"]
["⑵","城区澄阳街道控源截污工程","2017-2018",1700,"对澄阳街道进行控源截污建设和改造",1700,"完成",2018.01,"区水利局","区水务集团、开发区 "]
["⑶","城区黄桥街道控源截污工程","2017-2018",3000,"对黄桥街道进行控源截污建设和改造",3000,"完成",2018.01,"区水利局","区水务集团、黄桥街道"]
[17,"城区防洪及河道畅流工程","2017-2019",28200,"新建6座闸站（其中1座改建），整治25条河道，打通3处节点",10700,"新建5座闸站（其中1座改建），整治14条河道，打通3处节点。完成水下工程部分验收",2017.12,"区水利局","区水务集团"]
[18,"污水处理工程",null,81320,null,23000,null,null,"区水利局","区水务集团、所涉镇（区、街道） "]
["⑴","澄阳污水处理有限公司增建1万吨生活污水处理工程","2018-2019",2320,"扩建1万吨/日",1000,"完成土建工程","2018.06","区水利局","阳澄湖镇"]
["⑵","北桥一泓污水处理厂改扩建及有机污泥处理处置项目工程","2018-2020",38000,"提标2万吨/日、扩建2万吨/日,处理220吨有机污泥（200吨餐厨垃圾20吨地沟油）及配套工程",2000,"开工建设","2018.12","区水利局、城管局","区水务集团"]
["⑶","漕湖污水处理厂扩建工程","2018-2020",27000,"扩建6万吨/日",6000,"开工建设，完成深基坑支护结构","2018.09","区水利局","区水务集团"]
["⑷","相城区污水管网工程",2018,14000,"建设污水管网62公里",14000,"完工","2018.01","区水利局","区水务集团、各镇（街道）"]
[19,"相城区污水处理厂提标改造工程","2017-2018",20000,"对全区污水处理厂厂内设备设施及厂外一企一管等进行提标改造",18000,"完成",2017.1,"区水利局","区水务集团"]
[20,"老安置小区综合改善提升工程",null,8282,"对5个小区（登云家园、泰元家园二期、安元一期、安元二期、玉莲新村）进行道路管线、绿化景观、雨污水分流、技防等改善提升",7782,"全部建设完成",null,"区住建局、公安分局","开发区、高新区（筹）、元和街道"]
["⑴","登云家园改造\n（澄阳街道）",2018,1600,"老安置小区改造，包括小区立面、楼道、车位、弱电、雨污水分流、监控等",1200,"建设完成",2018.06,"区住建局、公安分局","开发区"]
["⑵","泰元家园二期改造\n（澄阳街道）",2018,1100,"老安置小区改造，包括小区立面、楼道、车位、弱电、雨污水分流、监控等",1000,"建设完成",2018.06,"区住建局、公安分局","开发区"]
["⑶","安元一期改造项目（元和街道）",2018,453,"进行立面、雨污水管道、绿化等设施进行改造等",453,"建设完成",2018.01,"区住建局","元和街道"]
["⑷","安元二期改造项目（元和街道）",2018,601,"进行立面、雨污水管道、绿化等设施进行改造等",601,"建设完成",2018.01,"区住建局","元和街道"]
["⑸","玉莲新村综合改造（高新区（筹））",2018,4528,"屋面防水施工、楼道公共部位维修、外立面改造、道路改造、景观绿化改造、新增天然气管道、雨污分流、安防一期工程",4528,"建设完成",2018.03,"区住建局、公安分局","高新区（筹）"]
[21,"绿化建设工程",null,20000,null,10000,null,null,"区园林绿化办","区园林绿化办"]
["⑴","书香公园建设工程","2017-2018",10000,"建设书香主题文化公园,配合苏州第二图书馆建设工程，连接相城第三中学与沈思港小学，建设开放型的市民公园，包含绿化工程、景观工程、安装工程与智能系统",6000,"建设完成",2017.09,"区园林绿化办","区园林绿化办"]
["⑵","黄蠡路绿化工程",2018,2000,"建设黄蠡路绿化工程，主要建设道路中分带、侧分带及两侧红线内的绿化景观，南侧沿河结合张庄河建设滨水景观",2000,"建设黄蠡路（广济路-御窑路）景观绿化",{"v":2018.02,"d":"2018"},"区园林绿化办","区园林绿化办"]
["⑶","平门塘（外国语学校段）景观工程","2018-2020",8000,"建设平门塘（外国语学校段）景观工程，工程主要建设平门塘两岸景观绿化，建设慢行系统等",2000,"实施平门塘（玉成河-朝阳河）景观绿化",{"v":2018.04,"d":"2018"},"区园林绿化办","区园林绿化办"]
[22,"城乡生活垃圾治理工程",2018,{"v":701.5,"d":"702"},"新增村（社区）垃圾收集点4个、新增垃圾清运车辆20辆、清洗扫路车3辆、铲车1辆、资源处理机1台,新增居住小区垃圾分类投放设施14个",{"v":701.5,"d":"702"},"完成",{"v":2018.05,"d":"2018"},"区城管局","所涉镇（区、街道） "]
["⑴","城乡生活垃圾治理工程（开发区）",2018,64,"观塘社区垃圾收集点1个、清运车辆1辆、新增分类小区永昌泾花苑、南亚小区、观塘社区、泰元社区、登云社区、徐庄社区",64,"完成",{"v":2018.07,"d":"2018"},"区城管局","开发区"]
["⑵","城乡生活垃圾治理工程（度假区）",2018,46,"莲花岛移建垃圾收集点1个、新增垃圾清运车2辆、分类小区湖畔花苑二区",46,"完成",{"v":2018.05,"d":"2018"},"区城管局","度假区"]
["⑶","城乡生活垃圾治理工程（高铁新城）",2018,190,"新增垃圾清运车1辆、清扫车3辆、铲车1辆",190,"完成",{"v":2018.09,"d":"2018"},"区城管局","高铁新城"]
["⑷","城乡生活垃圾治理工程（元和街道）",2018,172,"新增垃圾分类小区御苑家园（西区）、绿色时光（西区）、华美家园一期、垃圾清运车辆8辆",172,"完成",{"v":2018.06,"d":"2018"},"区城管局","元和街道"]
["⑸","城乡生活垃圾治理工程（黄桥街道）",2018,8,"垃圾分类小区三角咀二期",8,"完成",{"v":2018.06,"d":"2018"},"区城管局","黄桥街道"]
["⑹","城乡生活垃圾治理工程（渭塘镇）",2018,71,"新增垃圾清运车3辆、分类小区俪珠华庭",71,"完成",{"v":2018.06,"d":"2018"},"区城管局","渭塘镇"]
["⑺","城乡生活垃圾治理工程（高新区（筹））",2018,{"v":45.5,"d":"46"},"新增古宫社区垃圾收集点1个、垃圾清运车2辆、分类小区古宫社区",{"v":45.5,"d":"46"},"完成",{"v":2018.06,"d":"2018"},"区城管局","高新区（筹）"]
["⑻","城乡生活垃圾治理工程（阳澄湖镇）",2018,80,"新增枪堂村垃圾收集点1个、垃圾清运车2辆、资源处理机1台",80,"完成",{"v":2018.06,"d":"2018"},"区城管局","阳澄湖镇"]
["⑼","城乡生活垃圾治理工程（望亭镇）",2018,25,"新增垃圾清运车1辆、垃圾分类小区丽都阳光小区",25,"完成",{"v":2018.06,"d":"2018"},"区城管局","望亭镇"]
["五","社会保障水平提升工程",null,1302778,null,273870]
[23,"棚户区改造项目",null,1285517,"2018年棚户区续建、新建19个项目，建筑面积350.12万平方米，23570套。其中续建项目8个项目建筑面积130.59万平方米，9197套；新建项目11个建筑面积219.53万平方米，14373套",256609,null,null,"区住建局","所涉镇（区、街道） "]
["⑴","洞字花苑拆迁安置小区（二批）","2018-2020",65000,"建筑面积约18.7万平方米，含7幢高层，共1264套",18000,"完成基础施工","2018.11","区住建局","太平街道"]
["⑵","中环快速路春申湖路拆迁安置小区一期","2018-2020",57050,"建筑面积约16.3万平方米，住宅1040套",15000,"主体施工","2018.03","区住建局","黄桥街道"]
["⑶","永昌泾花园三期","2018－2021",110000,"建筑面积约32.6万平方米，2165套",10000,"基础施工","2018.10","区住建局","开发区"]
["⑷","盛北花园九期一标","2018－2021",100426,"建筑面积约15.12万平方米，680套",10000,"基础施工","2018.10","区住建局","开发区"]
["⑸","康阳新村二期二标段","2018-2020",16928,"建筑面积约4.5万平方米，408套",7617,"完成主体施工",2018.03,"区住建局","高新区（筹）"]
["⑹","新阳新村一期二标段","2018-2020",15058,"建筑面积约4万平方米，362套",7227,"完成主体施工",2018.03,"区住建局","高新区（筹）"]
["⑺","古宫新村三期","2018-2021",99330,"建筑面积约25.8万平方米，约2000套",4820,"基础施工","2018.10","区住建局","高新区（筹）"]
["⑻","新阳新村二期","2018-2021",35805,"建筑面积约9.3万平方米，730套",1745,"基础施工","2018.10","区住建局","高新区（筹）"]
["⑼","华元家园","2017－2021",94400,"项目新建总建筑面积约23.6万平方米，1580套；主要建设内容：住宅及配套商业",6000,"基础施工","2018.09","区住建局、元和街道","区城投集团"]
["⑽","五众泾花园","2017－2021",206520,"建筑面积约51.63万平方米，3116套；主要建设内容：住宅及配套商业",10000,"基础施工","2018.09","区住建局、元和街道","区城投集团"]
["⑾","珍珠花园一期","2018-2020",80000,"建筑面积约17.98万平方米，其中住宅约 13.2万平方米，约1028套",20000,"主体施工",2018.06,"区住建局","渭塘镇"]
["⑿","钻石家园三期","2017-2020",60000,"建筑面积19.54万平方米，其中住宅17.84万平方米，1430套",20000,"主体施工","2018.02","区住建局","渭塘镇"]
["⒀","洞字花苑拆迁安置小区（一批）","2017-2019",64000,"建筑面积18.9万平方米，共1264套",30000,"完成装饰施工","2017.01","区住建局","太平街道"]
["⒁","果园新村三期","2016－2018",28000,"建筑面积9.8万平方米，612套",13000,"完成主体施工","2016.11","区住建局","望亭镇"]
["⒂","三角咀家园三期一标","2015－2018",28000,"建筑面积13.65万平方米，879套",2200,"完成竣工验收","2015.10","区住建局","黄桥街道"]
["⒃","三角咀家园三期二标","2017－2019",23000,"建筑面积9.9万平方米，796套",15000,"完成主体施工","2017.09","区住建局","黄桥街道"]
["⒄","永昌泾花园二期","2016－2019",80000,"建筑面积22万平方米，1596套",32000,"完成主体施工","2016.10","区住建局","开发区"]
["⒅","盛北六期东区","2016－2019",32000,"建筑面积9.5万平方米,804套",4000,"完成竣工验收",2016.11,"区住建局","开发区"]
["⒆","朱巷三期四、五标段","2016－2019",90000,"建筑面积约27.3万平方米，1816套；主要建设内容：住宅及配套商业",30000,"完成主体施工","2016.04","区住建局","区城投集团"]
[24,"社保待遇提升工程",2018,16000,"稳步提升城镇职工养老金待遇、稳步提升城乡居民养老保险待遇、被征地农民征地保养金待遇水平；实施长期护理医疗保险",16000,"第一季度：国家公布养老金调整方案；组织实施1000万长期护理医疗保险；第二季度：省市出台养老保险退休人员调资政策;组织实施1000万长期护理医疗保险;第三季度：提高被征地农民征地保养金待遇、城保养老金待遇9000万；组织实施1000万长期护理医疗保险第四季度：提高被征地农民征地保养金待遇、城保养老金待遇3000万;组织实施1000万长期护理医疗保险",2018.01,"区人社局","区人社局"]
[25,"提升养老服务设施",2018,1261,"新(改)建镇（街道）养老服务中心1家、村（社区）日间照料中心13家，至年底每千名老人拥有各类养老床位数达46.4张",1261,"完成",null,"区民政局","所涉各镇（街道）"]
["⑴","北桥街道养老服务中心",2018,330,"建设面积约1000平方米的养老服务中心",330,"年内完成建设",2018.06,"区民政局","北桥街道"]
["⑵","日间照料中心建设（北桥街道）",2018,80,"庄基日间照料中心建设",80,"年内完成建设",2018.06,"区民政局","北桥街道"]
["⑶","日间照料中心建设（元和街道）",2018,50,"朱巷日间照料中心建设",50,"年内完成建设",2018.06,"区民政局","元和街道"]
["⑷","日间照料中心建设（元和街道）",2018,50,"古巷日间照料中心建设",50,"年内完成建设",2018.06,"区民政局","元和街道"]
["⑸","日间照料中心建设（元和街道）",2018,75,"凌浜日间照料中心建设",75,"年内完成建设",2018.06,"区民政局","元和街道"]
["⑹","日间照料中心建设（元和街道）",2018,50,"依云水岸日间照料中心建设",50,"年内完成建设",2018.06,"区民政局","元和街道"]
["⑺","日间照料中心建设（黄桥街道）",2018,26,"方浜日间照料中心建设",26,"年内完成建设",2018.06,"区民政局","黄桥街道"]
["⑻","日间照料中心建设（渭塘镇）",2018,20,"凤凰泾日间照料中心建设",20,"年内完成建设",2018.06,"区民政局","渭塘镇"]
["⑼","日间照料中心建设（阳澄湖镇）",2018,80,"消泾日间照料中心建设",80,"年内完成建设",2018.06,"区民政局","阳澄湖镇"]
["⑽","日间照料中心建设（高新区(筹)）",2018,200,"青阳日间照料中心建设",200,"年内完成建设",2018.08,"区民政局","高新区（筹）"]
["⑾","日间照料中心建设（高新区(筹)）",2018,100,"裴圩日间照料中心建设",100,"年内完成建设",2018.08,"区民政局","高新区（筹）"]
["⑿","日间照料中心建设（澄阳街道）",2018,50,"登云日间照料中心建设",50,"年内完成建设",2018.06,"区民政局","澄阳街道"]
["⒀","日间照料中心建设（度假区）",2018,50,"莲花村日间照料中心建设",50,"年内完成建设",2018.06,"区民政局","度假区"]
["⒁","日间照料中心建设（高铁新城）","2018－2019",100,"常楼日间照料中心建设",100,"年内完成建设",2018.06,"区民政局","高铁新城"]
[26,"困难群体帮扶","2018－2020",null,"充分利用现有政策、整合各类资源，力争用3年时间帮助全区4166户困难家庭的人均纯收入达到2万元",null,"年内完成955户困难群体脱困",null,"区民政局","区民政局"]
["六","公共服务提升工程",null,25578,null,18303]
[27,"路网通达工程",2018,20790,"新辟优化公交线路5条，购置新能源公交车35辆；建设公交场站 1个；城区排堵促畅工程、县道危桥改造",13515,null,null,"区交运局","区公共交通公司、区交投集团 、区交通运输行管中心"]
["⑴","公交优化",2018,3750,"新辟优化公交线路5条、2018年计划购置新能源公交车35辆",3750,"2018年8月份启动，年内完成全部购车计划",2018.08,"区交运局","区公共交通公司"]
["⑵","建设公交场站",2018,600,"阳澄湖镇客运站工程：公交首末站占地面积6000平方米，建筑面积约1000平方米，公交停车面积约3500平方米",600,"完成阳澄湖镇客运站工程\n",2018.05,"区交运局","区交投集团 "]
["⑶","排堵促畅工程","2017－2019",12500,"黄蠡路（广济北路-金砖路）、澄和路(东六路-东八路)新建工程、阳澄湖中路完善工程、支二路、支三路、相四路",7100,"黄蠡路（广济北路-金砖路）完成平门塘桥梁主体结构施工，完成其余段落路基施工、完成澄和路(东六路-东八路)新建工程、阳澄湖中路完善工程、支二路、支三路、相四路",2018.01,"区交运局","区交投集团 "]
["⑷","相城区2018度县道危桥改造工程","2018-2019",3940,"相城区阳元线、锡黄线、丰阳线三条县道7座三类桥梁的维修加固或改建",2065,"拆除新建的桥梁，完成半幅桥梁的桩基础、盖梁、箱梁安装及桥面施工，箱梁预制全部完成；维修加固的桥梁全部完工","2018.05","区交运局","区交通运输行管中心"]
[28,"厕所提升工程",2018,1328,"新建和改扩建7座旅游厕所、25座公共厕所",1328,"完成7座旅游厕所、25座公共厕所的新建和改扩建",2018.01,"区旅游局、城管局","区生态公司、开发区、度假区、元和街道、北桥街道、太平街道、黄桥街道、渭塘镇、高新区（筹）、阳澄湖镇、望亭镇"]
["⑴","旅游厕所提升",2018,361,"对高新区（筹）1座（冯梦龙村）、度假区3座（集散中心）、太平街道1座（荻西仓）、盛泽湖2座（月季公园）新建和改扩建",361,"完成7座旅游厕所的新建、改扩建",2018.01,"区旅游局","区生态公司、高新区（筹）、度假区、太平街道"]
["⑵","公共厕所提升",2018,967,"对开发区5座（漕湖湿地公园、卫渭路汽车站西侧、漕湖大道加油站东侧、澄园、桂花公园）、度假区3座（沺泾社区小桥浜南岸、湖畔社区农贸市场北侧、澄苑街农贸市场对面）、元和街道3座（待定）、北桥街道2座（农贸市场边、金家弄）、太平街道2座（太平街道老街、老街粮仓）、黄桥街道2座（永芳路、华元路）、渭塘镇2座（渭星街菜场内、玉盘路珍珠湖路）、高新区（筹）1座（东桥人民路长发路口）、阳澄湖镇2座（枪堂村陆家浜、消泾村十善村）、望亭镇3座（王家港、人民街小游园、老农贸市场）公共厕所新建和改扩建　",967,"完成25座公共厕所新建、改扩建",{"v":2018.05,"d":"2018"},"区城管局","开发区、度假区、元和街道、北桥街道、太平街道、黄桥街道、渭塘镇、高新区（筹）、阳澄湖镇、望亭镇"]
[29,"区信息化工程",null,3460,null,3460,null,null,"区政法委、经信局、政务办","区经信局、政务办、政法委、城管局、信访局、民政局、公安分局"]
["⑴","工业企业资源集约利用平台（相城区工业大数据平台）",2018,875,"建设工业大数据平台，建成数据上报、信息查询统计、企业分类、数据应用分析以及后台管理等功能在内的大数据系统；建设包括审批办证管理、证明管理系统、政务公开系统等政务“一张网”系统及后台管理软件系统。形成数据交互共享体系",875,"完成",2018.04,"区经信局、政务办","区经信局、政务办"]
["⑵","政务资源整合共享建设与服务",2018,560,"完成2018年相城区遥感影像航飞和制作，为全区政务数据资源整合共享提供专业运营服务，包括标准规范制定、技术咨询、数据加工处理、系统平台对接、资源目录构建、数据融合分析、日常事务管理等",560,"完成",2018.04,"区经信局","区经信局"]
["⑶","社会综合治理联动平台",2018,2025,"完成社情民意平台三期建设；实现创新基础上对12345平台进行改造升级；结合公安社会面治安监控建设，达到全面支撑相城区综合治理联动的应用需求",2025,"完成",2018.04,"区政法委","区政法委、城管局、信访局、民政局、公安分局"]

{"sheet":"空白表","index":1,"n_rows":17,"n_cols":11,"rows_kept":17,"hidden":true,"merged":[[0,0,0,9]],"flags":["formulas_cached_only"]}
["相城区2018年政府实事工程、重点项目计划实施项目表"]
["序号","项目名称","建设起止年限","计划总投资（万元）","项目规模及主要内容","2018年计划投资（万元）","2018年实施内容及完成形象进度","计划实施时间(年月）","主办单位","实施单位","备注"]
[1]
["⑴"]
["⑵"]
["⑶"]
["∶"]
[2]
["⑴"]
["⑵"]
["⑶"]
["∶"]
[3]
["⑴"]
["⑵"]
["⑶"]
["∶"]

{"sheet":"拍而未建工业项目","index":2,"n_rows":26,"n_cols":11,"rows_kept":26,"hidden":true,"merged":[[0,0,0,9]],"flags":["formulas_cached_only"]}
["相城区拍地未开工工业项目（列入2018年重点工业项目除外）"]
["序号","项目名称","建设起止年限","计划总投资（万元）","项目规模及主要内容","2018年计划投资（万元）","2018年实施内容及完成形象进度","计划实施时间(年月）","主办单位","实施单位","备注"]
[1,"苏州圆德经济发展有限公司","2018-2019",10000,"高端标准厂房，占地8亩，建设14000平米厂房",3000,"厂房建设完成20%",2018.06,"开发区","苏州圆德经济发展有限公司","开发区"]
[2,"吴通控股集团股份有限公司","2017-2018",120000,"达产后预计产值3亿元，大数据中心的建设，占地40.93亩，建设30000平米厂房","20000","厂房装修、设备安装","2017.10","开发区","吴通控股集团股份有限公司","开发区"]
[3,"苏州禾润昌新材料有限公司","2017-2018",30000,"达产后预计产值5亿元，主要生产高分子改性材料及功能性母粒，占地68.3亩，建设40000平米厂房","22000","厂房装修、设备安装",2017.09,"开发区","苏州禾润昌聚合材料股份有限公司","开发区"]
[4,"江苏凯尔生物识别科技有限公司","2018-2019",40000,"达产后预计产值15亿元，主要生产指纹识别模组，占地44亩，建设30000平米厂房",2000,"厂房建设完成20%",2018.06,"开发区","江苏凯尔生物识别科技有限公司","开发区"]
[5,"苏州北桥染色有限公司","2018-2019",1100,"高端标准厂房，占地6.7亩，建设10000平米厂房",800,"厂房建设完成20%",2018.04,"开发区","苏州北桥染色有限公司","开发区（北桥）"]
[6,"锦峰工业园","2018-2019",1700,"高端标准厂房，占地17.44，建设17000平米厂房",1500,"厂房建设完成20%",2018.04,"开发区","苏州锦峰工业发展有限公司","开发区（北桥）"]
[7,"苏州未来电器有限公司","2018-2019",2000,"占地5亩，建设5000平米厂房，主要生产智能终端电器和微型断路器，达产后预计产值3000万元",1000,"厂房建设完成10%",2018.06,"开发区","苏州未来电器有限公司","开发区（北桥）"]
[8,"苏州利德精工制造有限公司","2018-2019",30000,"占地51亩，建设71000平米厂房，主要生产生产、销售中央空调压缩机等，达产后预计产值1亿元",5000,"厂房建设完成30%",2018.03,"开发区","苏州利德精工制造有限公司","开发区（北桥）"]
[9,"山川丽（苏州）环保科技有限公司","2018-2019",10000,"占地16.8亩，建设8000平米厂房，主要生产印染污泥无害化处理，达产后预计产值0.5亿元","3000","厂房建设完成30%","2018.05","开发区","山川丽（苏州）环保科技有限公司","开发区（北桥）"]
[10,"苏州佳辉化工有限公司","-",11000,"4.5万吨/年制剂加工项目","-","回购完成","-","高新区（筹）","苏州佳辉化工有限公司","高新区（筹）"]
[11,"苏州华峰液化天然气有限公司","-",5000,"液化天然气储罐及配套项目","-","回购完成","-","高新区（筹）","苏州华峰液化天然气有限公司","高新区（筹）"]
[12,"苏州市野金不锈钢有限公司","2018-2019",9000,"年产不锈钢保温杯5万只，不锈钢厨具5万套；新增建筑面积34253平方米",6000,"厂房建设完成50%",2018.06,"高新区（筹）","苏州市野金不锈钢有限公司","高新区（筹）"]
[13,"翊腾机械（苏州）有限公司","2017-2018",10000,"生产用房12000平方米，年产年产压缩机、无油压缩机及压缩机零配件1000 台（套），观光车、高尔夫球车、电动汽车零配件400台（套）， 编织布60000条",9000,"竣工投产",2017.12,"高新区（筹）","翊腾机械（苏州）有限公司","高新区（筹）"]
[14,"苏州市非凡城市文化传播有限公司","2016-2019",18000,"设计街区1号地块（南天成路北、澄阳路东），占地13.1亩，容积率≤4.3，科教(文化创意)用地，地上建筑面积36816平方米，地下建筑面积7254平方米",10000,"地下两层及主体结构施工至6层。",2018.01,"高铁新城","苏州非凡城市文化传播有限公司"]
[15,"苏州高清传媒科技发展有限公司","2016-2019",8000,"设计街区2号地块（南天成路北、澄阳路东），占地7.11亩，容积率≤3，科教(文化创意)用地，地上建筑面积18700平方米，地下建筑面积3850平方米",8000,"主体封顶，装修完成，竣工验收。",2017.08,"高铁新城","苏州高清传媒科技发展有限公司","\n已开工"]
[16,"苏州傲英网络科技有限公司","2016-2019",8000,"设计街区3号地块（南天成路北、澄阳路东），占地8.64亩，容积率≤3，科教(文化创意)用地，地上建筑面积17280平方米，地下建筑面积3863平方米",6000,"主体封顶。",2018.03,"高铁新城","苏州傲英网络科技有限公司"," "]
[17,"苏州波发特通讯技术股份有限公司","2017-2018",21000,"建设年产3亿元基站射频天线，新增厂房4万平米",19000,"厂房、设备建设完成，项目投产",2017.12,"太平街道","太平街道","高铁太平"]
[18,"苏州温彻机电有限公司（威尔廉）","2018-2019",18000,"建设年产1万台木工机器人，新增厂房3.2万平方米",10000,"厂房土建结顶",2018.01,"渭塘镇","苏州温彻机电有限公司（威尔廉）","渭塘"]
[19,"苏州联胜化学有限公司","2018-2019",11000,"建设年仓储有机硅油3万吨，新增厂房1.4万平方米",6000,"厂房建设完成50%",2018.01,"渭塘镇","苏州联胜化学有限公司","渭塘"]
[20,"华环（苏州）汽车科技有限公司","2018-2019",10000,"建设年产50万套汽车排气系统及轻量化零部件",5000,"厂房建设完成50%",2018.03,"渭塘镇","华环（苏州）汽车科技有限公司","渭塘"]
[21,"大友（苏州）风洞技术有限公司","2018-2020",30000,"建设年可试验1500辆，新增厂房1.4939万平方米",10000,"厂房建设完成30%",2018.06,"渭塘镇","大友（苏州）风洞技术有限公司","渭塘"]
[22,"苏州富丽华教育科技有限公司","2017-2020",61350.37,"新建民办学校，位于朝阳河北、平门塘两侧，包括早教中心、6轨幼儿园，8轨小学，初中和高中。项目占地面积97614平米，建筑面积约11.6万平米",20000,"幼儿园及小学部分建设完成，投入使用；中学部分建设完成30%。",2017.09,"元和","苏州富丽华教育科技有限公司","元和"]
[23,"苏州杜威教育科技有限公司","2017-2018",5980.44,"新建民办幼儿园，位于文灵路东，建元路北，项目占地地面积13563平方米，总建筑面积13998.97平方米",5000,"建设完成，投入使用",2017.11,"元和","苏州杜威教育科技有限公司","元和"]
[24,"苏州市怡泰智能装备有限公司","2017-2018",15000,"新建2.67万平方米厂房",10000,"装修完成",2017.11,"望亭","苏州市怡泰智能装备有限公司","望亭"]

{"sheet":"审而未供工业项目","index":3,"n_rows":13,"n_cols":11,"rows_kept":13,"hidden":true,"merged":[[0,0,0,9]],"flags":["formulas_cached_only"]}
["2017通过预审项目未供地项目汇总（列入2018年重点工业项目除外）"]
["序号","项目名称","建设起止年限","计划总投资（万元）","项目规模及主要内容","2018年计划投资（万元）","2018年实施内容及完成形象进度","计划实施时间(年月）","主办单位","实施单位","备注"]
[1,"苏州康盛风电有限公司阳澄湖低风速风力二期工程项目","2018.4-2019.3",40000,"安装21台装机容量2000KW/台的发电机组，3台2500KW/台的发电机组",28000,"设备建设完成70%。",2018.4,"阳澄湖镇","苏州康盛风电有限公司","阳澄湖"]
[2,"苏州耀东信息设备有限公司金融机具研发生产与运营项目","2018-2020",12000,"建设年产11.25亿元银行机具，新建厂房3.5万平米",2000,"报建办理施工许可证",2018.11,"太平","苏州耀东信息设备有限公司","太平"]
[3,"波发特年产25万件基站射频天线项目","2018-2019",10000,"建设年产1亿元基站射频天线，新增厂房2万平米",3000,"厂房建设完成20%",2018.11,"太平","苏州波发特通讯技术股份有限公司","太平"]
[4,"苏品文化","2019-2020",11000,"建设产品展示及体验馆、研发中心、中式文化交流中心（博物馆），新增厂房5万平方米",800,"完成拍地，报建前期工作",2019.03,"渭塘镇","苏州市苏品家具有限公司","渭塘"]
[5,"中信检测","2019-2020",10000,"建设汽车零部件检测实验室、车内有害物质检测实验室和车用电器检测实验室，新增产房2万平方米",500,"完成拍地，报建前期工作",2019.03,"渭塘镇","苏州市中信节能与环境监测研究发展中心有限公司","渭塘"]
[6,"三维精密机械","2019-2020",15000,"建设年产精密汽车模具100套，汽车核心精密零部件8000万套，新增厂房1.5万平方米",500,"完成拍地，报建前期工作",2019.1,"渭塘镇","苏州三维精密金属制品有限公司","渭塘"]
[7,"苏州市斯可源自动化科技有限公司","2018-2019",15000,"年产5轴悬臂机械手100台、自动化治具1万套，数控机床设备1200台。总建筑面积16000平方米。",2000,"厂房建设完成20%",2018.8,"望亭","苏州市斯可源自动化科技有限公司","望亭"]
[8,"东莞市乔锋机械有限公司","2018-2019",16000,"年产数控立车960台，配置治具1000套，总建筑面积2.4万平方米。",2000,"厂房建设完成20%",2018.8,"望亭","东莞市乔锋机械有限公司","望亭"]
[9,"江苏厚道数控科技有限公司","2018-2019",15000,"年产立式加工中心300台、龙门加工中心20台、钻孔攻牙机120台、高速雕铣机60台。总建筑面积22400平方米。",2000,"厂房建设完成20%",2018.8,"望亭","江苏厚道数控科技有限公司","望亭"]
[10,"苏州博卫源实业有限公司","2018-2019",10000,"建设工业（标准厂房二层）7300平方米",2000,"厂房建设完成20%",2018.8,"望亭","苏州博卫源实业有限公司","望亭"]
[11,"苏州捷富洁净材料有限公司","2018-2019",19700,"建设工业厂房20000平方米",2000,"厂房建设完成20%",2018.8,"望亭","苏州捷富洁净材料有限公司","望亭"]